## Sheet1
Task Name | Week 1 |  |  |  | Week 2 | Week 3 | Week 4
Planning & Research
Design (Figma Prototype)
Development (Frontend)
Development (Backend)
Product Upload & Content
Testing & Bug Fixing
Planning & Research | Week 1
Decide B2B Business Type and Concept
Identify Target Market
Research Sample B2B E-commerce Sites
List Key Features
Design (Figma Prototype) | Week 1 |  |  | Week 2
Information Architechture & User Flow
UI Design (Figma Mockup)
Design Approval
Development (Frontend) | Week 2 | Week 3
Build Static UI (HTML/CSS)
Develop Frontend Components
Implement Interactivity (JS)
Development (Backend) | Week 3 |  | Week 4
Database Design & Setup
API Development
Frontend Integration
Product Upload & Content | Week 4
Product Listing
Image Gathering & Editing
Category Assignment
Upload to Website
Content Review
Testing & Bug Fixing | Week 4
System Testing
Bug Identification
Bug Fixing
Re-Testing Fixed Bugs
Final Testing